## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Planning session | 30 minutes | 2024-05-18 | Setting priorities on tasks
Learning Vue (reading documentation) | 5 hours | 2024-05-19 | Learn the basics
Setting up the project | 3 hours | 2024-05-19 | Set up vue environment and basic project structure
Creating About page | 1 hour | 2024-05-20 | Creatimg html element and styling
Creating a header | 5hours 25 minutes | 2024-05-20 | I had problim with learning router-link whuch I used in header. I spend some tim to learn it.
Creating house page | 2 hours 40 minutes | 2024-05-20 | Creatimg html element, styling and easy js
Creating a search element | 1 hour 30 minutes | 2024-05-21 | Creatimg html element, styling and easy js
Creating filter element | 1 hour 15 minutes | 2024-05-21 | Creatimg html element and styling
Fixing mistakes | 1 hour | 2024-05-22 | Fixing misteks when my code stop working, making code more readable
Lerning reactivety | 2,5 hours | 2024-05-24 | Read documnetation and use it in my project
Сalling get API | 4 hours | 25-26/5/2024
Creat a search | 40 minutes | 2024-05-26
Creat sorting button | 50 minutes | 2024-05-26
Making application composiable | 1 hour 15 minutes | 2024-05-27 | Create composiable file for fetching data
Creating New Listing Page | 10 hours 40 minutes | 28-31/5/2024 | Creating html elements, css and js logic
Creating Delate Button | 1 house 10minutes | 2024-06-01
Making House link active when open Creat New Listing page | 1 hour 10 minutes | 2024-06-05
Creating no result animation | 1 hour 40 minutes | 2024-06-06
Fixing mistakes | 1 hour | 2024-06-06
Creating delete and edite button | 1 hour | 2024-06-09
Creating house details page | 5 hous | 2024-06-12
Creating recommendation in details page | 2 hours | 2024-06-13
Creating delete and edite buttons in deteils page | 2 hours 30 minutes | 2024-06-15
Confirmation delete window | 2 hours | 2024-06-16
Fixing file input and add validation when it's empty | 3 hours | 2024-06-17
Total amount of hours | 64